## Sheet1
quizzically (cost / time analysis of next steps)
First Step (Consolidation) |  |  |  |  | Notes
| To be completed |  |  |  |  | All times are based on 1 full time worker
|  | Consolidate current work into v3.0 Chaffinch |  |  |  | All costs are based on 1 full time worker
|  |  | Re-build Console v2.0 |  |  | All time and costs don't necessarily scale with more workers
|  |  | Re-build Mobile Web v2.0 |  |  | Once the first step is complete all others don't have a particular order
Re-build Mobile App v1.0
| Major Features |  |  |  | Time
|  | Basic tenants: Robust, Secure, Scalable, Self Explanatory |  |  |  | Remembering that during testing phases (which can all be done by Brian) we can move on with development
|  | Host a quiz |  |  |  | 8 Month Total Development Period
Take a quiz
|  | Question, Picture, Music rounds |  |  | Cost
|  | Leagues and League Quizzes |  |  |  | £20000 Total
Comments
|  | Once complete this will be a solid basic pub quiz experience |  |  | Final Comments
| Time |  |  |  |  | I'd aim to secure £30000 and then use that to deliver and advertise a shit hot system
|  | 1 month build |  |  |  | If we can build a user base we might be able to sell off this mother for a chunk of change
|  | 1 month test |  |  |  | I'd say based on this we'd should be trading by this autumn on a self explanatory system (no support)
| Cost |  |  |  |  | Then a year on from this Christmas we should be eyeing up locking up market share with a full system
£2500 based on £2500 a month
Testing months done in house
Second Step (Location versus Location)
To be completed
v4.0 Dickcissel
Ability to challenge locations
Ability to make and accept open challenges
Communication channel for multiple locations
Ability to take control of quiz or change the quiz master
Ability to score locations effectively against each other
Major Features
Location versus location quizzes
Communicate between locations
Comments
Perhaps different pricing for challenge quizzes?
Maybe challenger pays all fees?
Time
2 month build
2 month test
Cost
£5000 at £2500 a month
Third Step (Advertising)
To be completed
v5.0 Elegant Tern
Ability to include advertising
Ability to modify what advertising is used
Uploading images and text
Ability to chose when user sees the advertising
Write comments to facebook / twitter
Interact with facebook friends
Major Features
Advertising Management
Facebook Integration
Time
1 month build
1 month test
Cost
£2500 a month
Fourth Step (Multi-Media Questions)
To be completed
v6.0 Fox Sparrow
Different interaction types
Shake for answer
Multiple device answers
Fastest finger first on multiple devices
Swipe left for no or right for yes
Different question types
Puzzle questions
Video questions
Complete the lyric
Multiple person answers
NFC?
Major Features
Host of new question types
Time
2 month build
2 month test
Cost
£5000 at £2500 a month
Fifth Step (User Interactions)
To be completed
v7.0 Gadwall
Question economy accessed by quizmasters and players
Pulling questions from the internet (What Napier was supposed to deliver)
Quizmasters and players starting their own leagues
Major Features
Question economy
Finalizing Napier work
User based leagues
Time
2 month build
2 month test
Cost
£5000 at £2500 a month